|  | JANUARY | FEBRUARY |
| --- | --- | --- |
| Steering Committee & Full Council | Council Chair appoints committee chairs and membership Mentor/Mentee luncheon(s) to welcome new members Day-long Council Orientation – review annual Timeline of Critical Activities Set up training for Feb. Steering and Council Secure locations for all meeting rooms, including off-site Council meetings (July or Aug for Project LEAP) | 1st Steering Committee and Council meetings Training in Effective Meeting Management or other skills building training at Steering Committee Approve the annual Timeline of Critical Council Activities and distribute at all committee meetings and to the community |
| Affected Community | No meeting | ORIENTATION AT ALL COMMITTEE MEETINGS INCLUDING: Review goals & timeline Schedule outreach events (Road 2 Success, health fairs, etc.) in order to recruit Council applicants Elect a Vice Chair JOINT MEETING WITH QA TO SELECT CRITERIA |
| Comprehensive HIV Planning | No meeting unless working on a Needs Assessment or Comp Plan Start planning for the next Epi Profile | Review goals and timeline. Discuss all work products Elect a Vice Chair |
| Operations | Committee meets to fine tune January Council Orientation. Host Mentor/Mentee Luncheon Host Council Orientation Set up new external member ½ day orientation | Review goals & timeline. Discuss all work products Sign confidentiality forms Determine the monthly Council training schedule General review of policies and procedures, if necessary Conduct new external member orientation Elect a Vice Chair |
| Priority & Allocations | No meeting. | Committee orientation, including training to read AA reports. Review allocations based on actual grant award Approve Principles & Criteria, Priority Setting process and Unspent Funds policy. If necessary, review revised PC budget from Operations based on actual grant award JOINT MEETING WITH QA TO SELECT CRITERIA |
| Project LEAP | Advisory Committee meets to implement student recruitment plan. Release PR and application forms. | Recruit student applicants. Interview applicants. Secure speakers |
| Quality Assurance | No meeting Deadline for submitting Idea Forms | Joint meeting with P & A, Affected Community & others to establish criteria for selecting the service categories. Committee orientation, including training to read AA reports. |
| Office of Support | Submit ad with Council meeting dates (HRSA require.) Meet with AA’s to review annual Timeline. Reserve rooms for Public Hearings Organize HTBMN training. Secure speakers. | Submit ad with Council meeting dates (HRSA require.) Staff preps HTBMN workgroup materials. Invite community to submit input into subcategory allocations. |

|  | MARCH | APRIL |
| --- | --- | --- |
| Steering Committee & Full Council | Announce HTBMN Training APPROVE any documents needed for HTBMN (Needs Assessment? Comp Plan? Epi Profile?) and Criteria for Selecting Service Categories | After Council: - 3 hour training for How To Best Meet Need (HTBMN) decision-making documents & criteria. Council Training: HTBMN Process |
| Affected Community | Consumer Training on HTBMN process Schedule educational presentations for future meetings Review Comp Plan task list for this committee | NO MEETING – ATTEND HTBMN training & workgroup meetings |
| Comprehensive HIV Planning | Select two presentations for the Public Hearings Create recommendations from the Needs Assessment and/or Epi Profile for HTBMN Evaluation Workgroup conducts Comp Plan evaluation EIIHA Workgroup meets to discuss data needs for next EIIHA Strategy Review Comp Plan task list for this committee | NO MEETING - ATTEND HTBMN training & workgroup meetings Consider a special study if no new Needs Assess or Comp Plan |
| Operations | Review revised PC budget based on actual grant award and forward to P&A if necessary (due to AA in April) Review Comp Plan task list for this committee | NO MEETING - ATTEND HTBMN training & workgroup meetings |
| Priority & Allocations | May not need to meet | Attend HTNMN training & workgroup meetings COMMITTEE MEETS TO: Review funding requests for unspent monies Submit Quarterly Report of Committee activities Review Comp Plan task list for this committee |
| Project LEAP | Inform student applicants if accepted or not | Classes begin |
| Quality Assurance | PR for HTBMN IMPORTANT: Appoint & train HTBMN workgroup co-chairs RWGA presents: Chart Reviews, Client Satisfaction and Focus Group results. Approve checklist for assessing the administrative mechanism Review Comp Plan task list for this committee | NO MEETING - ATTEND HTBMN training & workgroup meetings |
| Office of Support | Create Conflict of Interest List for voting in HTBMN. Print 2014 – 2015 Blue Book? Release Subcategory Allocation Review memo – Feb. 14 | Prepare next year’s Office of Support Budget for the May Operations Committee meeting. Include Blue Book? Needs Assessment? Comp Plan? |

|  | MAY | JUNE |
| --- | --- | --- |
| Steering Committee & Full Council | Council Training: Priority Setting Process Approve unspent funds Provide letter from chair endorsing the revised allocations based on award. (May no longer be needed) | Approve next year’s service definitions. Project LEAP students present results of their needs assessments |
| Affected Community | MAY OR JUNE - Host the Public Hearing on How To Best Meet the Need recommendations. Submit Quarterly Report of Committee activities | Host the second Public Hearing on next year’s priorities and allocations. |
| Comprehensive HIV Planning | Review Council responsibilities in Comp Plan Develop presentation for the second Public Hearing | Revise the current Epi Report with complete data from DSHS? Ask Council to give the committee the authority to approve the new EIIHA strategy. |
| Operations | Operations Committee hosts HTBMN workgroup for Project LEAP & Blue Book. The committee reviews Council Support Budget (see policy). Submit Quarterly Report of Committee activities | Continue to review/revise policies and procedures if necessary. |
| Priority & Allocations | Approve next year’s priorities Create timeline for Part B/SS allocations if done separately. Organize a public hearing if done separately. Submit Quarterly Report of Committee activities | Hold special meetings to create next year’s allocations. Approve the allocations at the special meetings with final approval at the regularly scheduled June meeting. Public Hearing on next year’s recommended priorities & allocations. Special meeting to review public comment. |
| Project LEAP | Staff facilitate classes | Staff facilitate classes |
| Quality Assurance | Review the subcategory allocation request forms Approve next year’s HTBMN results Approve HIV Targeting Chart. Review subcategory allocation requests. Forward recommendations to P & A by June. Set date for Sept. joint meeting of P & A, QA and others to determine data needs for all committees next year. Operations may need changes in Oct. for MOU review. Public Hearing to review next year’s service definitions. Submit Quarterly Report of Committee activities Schedule Special Committee meeting to review public comment | Complete the assessment of the administrative mechanism & send recommended action to Steering. Review monthly AA reports. Deadline for submitting idea forms. |
| Office of Support | Every other year: begin updating Blue Book database |  |

|  | JULY | AUGUST |
| --- | --- | --- |
| Steering Committee & Full Council | Council Training: The Allocations Process Approve next year’s priorities and allocations. Approve the assessment of the administrative mechanism and recommended actions. | Approve anything else needed for the grant application Approve carryover funds. |
| EIIHA Workgroup | Approve target populations based approved criteria and new HRSA guidance? |  |
| Affected Community | Submit Quarterly Report of Committee activities | Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | Approve EIIHA Strategy? Submit Quarterly Report of Committee activities | Approve EIIHA Strategy? Continue to work on Comp Plan, Needs Assessment or special studies |
| Operations | Submit Quarterly Report of Committee activities | No meeting. |
| Priority & Allocations | If necessary, fix problems Council has with recommended priorities and allocations for next year. Allocate carryover funds. Submit Quarterly Report of Committee activities | No meeting |
| Project LEAP | Facilitate classes & host graduation | Ask Council Chair to appoint all LEAP graduates who apply for Council and committee membership as external committee members. |
| Quality Assurance | Meet only if needed to: review Idea forms submit Quarterly Report of Committee activities | No meeting. |
| Office of Support | RESERVE ROOMS FOR NEXT CALENDAR YEAR: ALL COUNCIL & LEAP MEETINGS Start working on Office of Support portions of the Part A grant application. | Work on Office of Support portions of the Part A application. |

|  | SEPTEMBER | OCTOBER |
| --- | --- | --- |
| Steering Committee & Full Council | Council reviews final draft of grant application. Chair submits letter of concurrence according to instructions in HRSA guidance. | Training: EIIHA Update and Intimate Partner Violence and HIV. Council Chair selects those who will receive the World AIDS Day Proclamation at Commissioners Court. |
| Affected Community | Standards of Care Training Host a Road 2 Success with info re: changes to RW funded services next year? JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | Consumer Only SOC Workgroup Meeting Submit Quarterly Report of Committee activities Conduct annual committee self-evaluation Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | Begin designing the next Needs Assessment or Comp Plan process. OR Continue to work on Comp Plan, Needs Assessment or special studies | Continue to work on Comp Plan, Needs Assessment or special studies. Submit Quarterly Report of Committee activities Conduct annual committee self-evaluation |
| Operations | Interview Council applicants Mail out copy of the MOU for input. Draft a tool for Council’s self-evaluation in November Joint Meeting of P & A, QA and others to dialogue about data needs for next year. Operations needs in Oct. | Interview Council applicants Ask stakeholders if they wish to revise/revisit the MOU. Begin to organize December election of officers Begin to organize the January Council Orientation Submit Quarterly Report of Committee activities Conduct annual committee self-evaluation |
| Priority & Allocations | No meeting JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | Allocate unspent funds. Make plan for carryover funds. Due to HRSA in Dec. Submit Quarterly Report of Committee activities Since this is usually the last meeting of the year, review the Committee goals for next year. Conduct annual committee self-evaluation |
| Quality Assurance | Deadline for Idea forms. Submit Quarterly Report of Committee activities JOINT MEETING WITH QA TO DETERMINE NEXT YEAR’S DATA NEEDS. | Participate in the Standards of Care and Performance Measure Work Groups. |
| Office of Support | Work with Judge’s Office on World AIDS Day Proclamation – Nov. presentation at Commissioners Court Draft a tool for Council’s self evaluation in November |  |

|  | NOVEMBER | DECEMBER |
| --- | --- | --- |
| Full Council | Approve unspent funds and plan for carryover funds. Recognize External Committee members. Conduct annual Council self-evaluation | Approve recommendations regarding next year’s Standards of Care and Performance Measures. Acknowledge everyone's hard work. Hold elections for next year’s RWPC Officers Chair begins to make committee appointments Chair begins to organize Mentor Luncheon for mid-January |
| Affected Community | Prepare for World AIDS Day events Host a Road 2 Success with info re: changes to RW funded services next year? | No meeting Host a Road 2 Success with info re: changes to RW funded services next year? |
| Comprehensive HIV Planning | Continue to work on Comp Plan, Needs Assessment or special studies | No meeting |
| Operations | Final recommendations to CEO re: Council applicants and next year’s appointees. Approve Project LEAP service definition | No meeting The County Judge announces next year’s Council appointments. Chair of Planning Council and Chair of Operations conduct Director’s Annual Performance Evaluation. |
| Priority & Allocations | No meeting | No meeting |
| Project LEAP | Prepare evaluation of this year’s Project LEAP Advisory Committee meets to review Evaluation, make recommendations on the service definition & create a plan for student recruitment. Create calendar for next year’s Project LEAP | Set up December or January Advisory Committee meeting to start recruiting student applicants. |
| Quality Assurance | Approve recommendations to next year’s Standards of Care and Performance Measures. Review Quarterly Reports from AAs Submit Quarterly Report of Committee activities Conduct annual committee self-evaluation | No meeting |
| Office of Support | Director works with CEO on new Council appointments that start January 1st. | HRSA meeting in Washington DC Manager conducts annual performance evaluation of all support staff. Manager creates next year’s Council Timeline of Critical Activities. Remind Council members to turn in receipts before Feb. 15th and March 30th. |

NEXT NEEDS ASSESSMENT – Collect data in 2019